## PROJECT_ESTIMATE
Category | Item | Description | Complexity | Hours | Rate (INR/hr) | Amount (INR)
Frontend Development | Home Page | Product listing, categories, search, filters, responsive design | High | 12 | 400 | 4800
Frontend Development | Product Detail Page | Product images, variants, specifications, reviews, buy now | High | 10 | 400 | 4000
Frontend Development | Cart & Checkout | Cart management, checkout flow, order summary | Medium | 8 | 400 | 3200
Frontend Development | User Authentication | Sign in, sign up, password reset, profile management | Medium | 6 | 400 | 2400
Frontend Development | User Dashboard | Order history, favorites, profile settings | Medium | 6 | 400 | 2400
Frontend Development | Admin Panel | Product management, order management, user approval | High | 10 | 400 | 4000
Frontend Development | Responsive Design | Mobile optimization, tablet views, cross-browser testing | Medium | 8 | 400 | 3200
Backend Development | Database Setup | Supabase setup, tables, relationships, RLS policies | High | 8 | 500 | 4000
Backend Development | Authentication System | User auth, admin roles, profile management | Medium | 5 | 500 | 2500
Backend Development | Product Management | CRUD operations, variants, stock management | High | 6 | 500 | 3000
Backend Development | Order System | Order creation, batch orders, stock updates | High | 8 | 500 | 4000
Backend Development | Email Notifications | Resend integration, order emails, templates | Medium | 4 | 500 | 2000
Features | Shopping Cart | Add to cart, quantity management, variant selection | Medium | 5 | 400 | 2000
Features | Buy Now | Direct purchase, variant selection, stock validation | Medium | 4 | 400 | 1600
Features | Favorites System | Add/remove favorites, favorites page | Low | 3 | 400 | 1200
Features | Product Search & Filter | Search functionality, category filters, sorting | Medium | 5 | 400 | 2000
Features | Product Reviews | Review system, ratings display | Low | 3 | 400 | 1200
Features | Stock Management | Variant-based stock, real-time updates | High | 6 | 500 | 3000
Features | Order Success Animation | Success popup, mobile optimization | Low | 2 | 400 | 800
UI/UX Design | Design System | Color scheme, typography, component library (shadcn/ui) | Medium | 6 | 350 | 2100
UI/UX Design | User Interface | Page layouts, navigation, user flows | Medium | 8 | 350 | 2800
UI/UX Design | Admin Interface | Admin dashboard, management screens | Medium | 4 | 350 | 1400
Testing & QA | Functionality Testing | Feature testing, bug fixes, edge cases | Medium | 8 | 300 | 2400
Testing & QA | Cross-browser Testing | Chrome, Firefox, Safari, Edge compatibility | Low | 3 | 300 | 900
Testing & QA | Mobile Testing | iOS, Android responsive testing | Low | 3 | 300 | 900
Testing & QA | Performance Testing | Load time optimization, database queries | Low | 2 | 300 | 600
Deployment | Vercel Setup | Deployment configuration, environment variables | Low | 2 | 400 | 800
Deployment | Supabase Configuration | Database, edge functions, webhooks, secrets | Medium | 3 | 400 | 1200
Deployment | Domain & SSL | Domain setup, SSL certificate (if required) | Low | 1 | 400 | 400
Documentation | Technical Documentation | Setup guide, API documentation, database schema | Low | 4 | 300 | 1200
Documentation | User Guide | Admin guide, feature documentation | Low | 2 | 300 | 400
Project Management | Planning & Meetings | Client meetings, requirement gathering, updates | Medium | 6 | 300 | 1800
Project Management | Version Control | Git setup, repository management, code reviews | Low | 2 | 300 | 400
Project Management | Bug Fixes & Support | Post-delivery support (1 month) | Medium | 8 | 300 | 1400
SUMMARY
[5 empty] | Total Development Hours | 171
[5 empty] | Total Project Cost (INR) | 70000
DISCOUNTED PRICING FOR CLIENT
[5 empty] | Base Cost | 70000
[5 empty] | Discount (42%) | -30000
[5 empty] | Final Project Cost | 40000

## MILESTONES
PAYMENT MILESTONES
Milestone 1 | Project Start (30%) | ₹12420
Milestone 2 | Frontend Complete (30%) | ₹12420
Milestone 3 | Backend & Testing Complete (30%) | ₹12420
Milestone 4 | Deployment & Handover (10%) | ₹4140
DELIVERABLES
1 | Complete E-commerce Website
2 | Admin Panel for Product & Order Management
3 | User Authentication & Profile System
4 | Shopping Cart & Checkout System
5 | Email Notification System
6 | Mobile Responsive Design
7 | Supabase Database Setup
8 | Vercel Deployment

## FEATURES
FEATURES INCLUDED | TECHNOLOGY STACK
Product Listing with Categories | Frontend | React Js + TypeScript + Vite
Product Search & Filters | UI Library | shadcn/ui + Tailwind CSS
Product Variants (Color/RAM/Storage) | Backend | Supabase (PostgreSQL)
Stock Management System | Authentication | Supabase Auth
Shopping Cart | Email Service | Resend API
Buy Now (Direct Purchase) | Hosting | Vercel
User Authentication | State Management | React Context + TanStack Query
User Profile & Settings
Order History
Favorites System | FOR FUTURE UPDATIONS
Product Reviews & Ratings | Payment Gateway Integration
Admin Product Management | Mobile Push Notifications
Admin Order Management | Multi-language Support
Email Notifications (Order Confirmation) | Advanced Analytics Dashboard
Responsive Design (Mobile/Tablet/Desktop) | Inventory Management System
Order Success Animations | Shipping Integration
Stock Validation | Custom Domain Purchase
Batch Order Processing | Logo Design